## Sheet1
Milestone Code | Milestone Name | Description | Category | Industry | Owner | Suggested Partner Type | Deliverables | Acceptance Criteria | Dependencies | SLA (days) | Evidence/Artifacts | Related KPIs | Stage | Risk Notes
INT.ERP.CONNECT | Connect Client ERP | Establish secure connection to client ERP and validate credentials. | Data & Integration | Cross-Industry | Ops Admin (HQ) | ERP | Connected ERP tenant; API keys vaulted; connectivity test report | Test sync succeeded; 0 critical auth errors | Client admin access | 3 | Connection log; screenshot; access approval | FIN.FORECAST_MAPE%, LOG.PERF_ORDER% | Plan Monitor | Rate limits; multi-entity complexity
INT.MAP.COA | Chart of Accounts Mapping | Map client COA to standard analytics categories. | Data & Integration | Cross-Industry | Finance Lead (HQ) | Accounting Firm | COA mapping file; exceptions list | ≥98% of GL accounts mapped; no double-count | INT.ERP.CONNECT | 5 | Mapping workbook; sign-off | FIN.GM%, FIN.OP_MARGIN% | Plan Monitor | Legacy codes; inconsistent usage
INT.MAP.MASTER | Master Data Mapping (Customers/Suppliers/SKUs) | Map customers, suppliers, SKUs, taxes, and warehouses. | Data & Integration | Cross-Industry | Ops Admin (HQ) | ERP | Master mapping tables; unmapped list | ≥95% coverage; duplicates resolved | INT.ERP.CONNECT | 7 | CSV mappings; dedupe log | WC.DSO, WC.DPO, INV.TURN | Plan Monitor | Duplicate entities; unit conversions
INT.DATA.QUALITY | Data Quality Baseline | Profile historical data for completeness, consistency, and outliers. | Data & Integration | Cross-Industry | Ops Admin (HQ) | ERP | DQ scorecard; remediation plan | All critical fields ≥ 95% completeness | INT.MAP.MASTER | 5 | DQ report; anomaly list | FIN.BUD_VAR_OPEX%, QTY.DEFECT_RATE% | Plan Monitor | Backfills needed
INT.SYNC.SCHED | Sync Schedule & Monitoring | Configure incremental sync cadence and alerting. | Data & Integration | Cross-Industry | Ops Admin (HQ) | ERP | Hourly/daily schedule; alert rules | ≥99% sync success weekly | INT.ERP.CONNECT | 2 | Scheduler config; alert tests | INT sync health | Plan Monitor | API quota
FIN.BASELINE | Financial Baseline | Compile baseline Rev/COGS/Opex and working capital metrics. | Finance | Cross-Industry | Finance Lead (HQ) | Accounting Firm | Baseline pack; reconciliation | Balances tie to GL; variance < 0.5% | INT.MAP.COA | 4 | Baseline workbook | FIN.GM%, WC.CCC | Plan Builder | Timing differences
FIN.AR.POLICY | AR Policy & Credit Limits | Standardize credit terms and set customer credit limits. | Finance | Cross-Industry | Finance Lead (HQ) | Accounting Firm | Credit policy; limit table | Policy approved; top 50 customers configured | FIN.BASELINE | 5 | Signed policy; ERP screenshots | WC.DSO, AR.AGING_90+% | Plan Monitor | Sales pushback
FIN.AP.TERMS | AP Terms Optimization | Negotiate supplier terms and early-payment discounts. | Finance | Cross-Industry | Finance Lead (HQ) | Accounting Firm | Terms matrix; negotiation notes | ≥10% suppliers on improved terms | FIN.BASELINE | 10 | Contracts; emails | WC.DPO, FIN.FCF | Plan Monitor | Supplier resistance
FIN.CASH.FORE | Cash Flow Forecast Setup | Implement 13-week direct cash flow model. | Finance | Cross-Industry | Finance Lead (HQ) | Accounting Firm | 13W forecast; variance logic | MAPE ≤ 10% for 4 weeks | FIN.BASELINE | 7 | Model; SOP | FIN.FCF, FIN.FORECAST_MAPE% | Plan Monitor | Data granularity
FIN.CLOSE.SOP | Month-End Close SOP | Define close checklist, owners, and timelines. | Finance | Cross-Industry | Finance Lead (HQ) | Accounting Firm | Close calendar; RACI | Close achieved ≤ D+5 | FIN.BASELINE | 5 | Checklist; sign-offs | FIN.BUD_VAR_REV% | Plan Monitor | Resource constraints
INV.COUNT.BI | Inventory Count (Baseline) | Perform opening cycle count/stock take and reconcile. | Inventory & Supply | Cross-Industry | Partner (Stock) | Accounting Firm | Count sheets; variance report | Discrepancies ≤ 1% value | INT.MAP.MASTER | 4 | Signed count; photos | INV.TURN, WC.DIO | Plan Monitor | Access windows
PUR.PLAN.SETUP | Purchase Plan Setup | Build purchase plan using recent sales + buffer. | Inventory & Supply | Cross-Industry | Ops Admin (HQ) | ERP | Purchase plan; reorder rules | Top 100 SKUs have coverage ≥ target | FIN.BASELINE | 6 | Plan file; ERP config | Stockout, INV.TURN | Plan Monitor | Lead time volatility
INV.NEAR.EXPIRY | Near-Expiry Program | Identify near-expiry items and discount list. | Inventory & Supply | Cross-Industry | Partner (Ops) | Implementation | Discount list; clearance plan | Exposure reduced by ≥50% in 30 days | INV.COUNT.BI | 3 | SKU list; approvals | Near-Expiry %, Refund Rate | Plan Monitor | Brand guidelines
RPT.DASH.LAUNCH | KPI Dashboard Launch | Deploy KPI dashboard with G/A/R thresholds. | Reporting & Governance | Cross-Industry | Ops Admin (HQ) | ERP | Live dashboard; threshold rules | All selected KPIs compute w/o error | INT.SYNC.SCHED | 3 | Screenshots; test cases | All selected | Plan Monitor | Mapping gaps
RPT.EXCEPT.RULES | Exception Rules Library | Configure variance/threshold alerts and routing. | Reporting & Governance | Cross-Industry | Ops Admin (HQ) | ERP | Rules set; notification matrix | Alerts fire with <1% false positives | RPT.DASH.LAUNCH | 2 | Rule export; tests | DSO, Stockout, MAPE | Plan Monitor | Alert fatigue
RPT.TEMPLATE | Report Templates (Exec/Ops/CFO) | Create branded templates with commentary slots. | Reporting & Governance | Cross-Industry | Finance Lead (HQ) | Accounting Firm | PDF/PPT/Excel templates | Approved by client CFO | RPT.DASH.LAUNCH | 2 | Template files | Top KPIs | Plan Monitor | Brand compliance
GOV.POLICY | Governance Policy & Approvals | Set policy for edits to targets/milestones and approvals. | Reporting & Governance | Cross-Industry | Ops Admin (HQ) | Implementation | Policy document; app config | Mode A/B/C set; audit trail enabled | RPT.TEMPLATE | 1 | Policy PDF; app screenshots |  | Plan Builder | Stakeholder alignment
MEET.CADENCE | Meeting Cadence & Calendar | Publish recurring review and action meetings. | Reporting & Governance | Cross-Industry | Ops Admin (HQ) | Training | Calendar invites; agendas | First 3 months scheduled | RPT.TEMPLATE | 1 | ICS; agenda |  | Plan Monitor | Attendee availability
TRN.CLIENT.APP | Client App Training | Train client users on CFO app, dashboards, and approvals. | Change & Training | Cross-Industry | Partner (Training) | Training | Training deck; recordings; Q&A | CSAT ≥ 90%; ≥ 80% attendance | RPT.DASH.LAUNCH | 2 | Attendance sheet; survey | CS.CSAT% | Plan Monitor | Language/time zones
TRN.PARTNER.ONBD | Partner Onboarding | Onboard and certify partner team on processes and SLAs. | Change & Training | Cross-Industry | Ops Admin (HQ) | Implementation | Certification; access granted | All roles active; SLA acceptance signed | GOV.POLICY | 2 | Certificates; forms | PS.ON_TIME% | Plan Builder | Partner capacity
RTL.CAT.MERCH | Category Merchandising Plan | Seasonal assortment & pricing calendar. | Sales & CRM | Retail & eCommerce | Client (Merch) | Implementation | Assortment matrix; price ladders | Top categories have plan & safety stock | PUR.PLAN.SETUP | 7 | Plan file | RTL.SELL_THROUGH%, FIN.GM% | Plan Monitor | Supplier MOQs
RTL.ECOM.CHECKOUT | Checkout Optimization Sprint | Reduce cart abandonment with UX fixes. | Sales & CRM | Retail & eCommerce | Partner (Digital) | Implementation | A/B tests; improved funnel | Cart abandon ↓ ≥ 10% | RPT.DASH.LAUNCH | 10 | Test results | RTL.CART_ABANDON% | Plan Monitor | Dev resources
CPG.ROUTE.OPT | Route-to-Market Optimization | Optimize coverage and frequency by outlet tier. | Operations | FMCG/Distribution | Partner (Ops) | Implementation | Route plan; outlet tiers | Visits aligned to ABC tiers | CPG.DISTR_REACH% | 6 | Maps; lists | CPG.DISTR_REACH%, CPG.CASE_FILL% | Plan Monitor | Field constraints
CPG.PROMO.CALENDAR | Promo Calendar & Claims Control | Set promo calendar and implement claims validation. | Sales & CRM | FMCG/Distribution | Finance Lead (HQ) | Accounting Firm | Promo calendar; claims SOP | Claim disputes ≤ 2% | CPG.PROMO_UPLIFT% | 5 | SOP; calendar | CPG.PROMO_ROI | Plan Monitor | Retailer buy-in
MFG.OEE.PROG | OEE Improvement Program | Define loss tree and kaizen backlog. | Operations | Manufacturing | Partner (Lean) | Implementation | Loss tree; kaizen list | OEE +3 pts in 60 days | MFG.OEE baseline | 15 | Workshop notes | MFG.OEE, MFG.SCRAP% | Plan Monitor | Ops buy-in
MFG.PM.SCHEDULE | Preventive Maintenance Schedule | Build PM plan for critical assets. | Operations | Manufacturing | Client (Maintenance) | Implementation | PM calendar; checklists | Critical assets on PM plan | MFG.CAP_UTIL% | 5 | PM system export | MFG.AVAIL% | Plan Monitor | Spare parts
LOG.SLOT.PUT | Slotting & Putaway Optimization | Re-slot fast movers and optimize putaway. | Operations | Logistics & Warehousing | Partner (WMS) | ERP | New slotting map; SOP | Picking time ↓ ≥ 8% | LOG.DOCK_TO_STOCK | 4 | Before/after KPIs | LOG.PICK_ACC%, LOG.ORDER_CYCLE | Plan Monitor | Space limits
LOG.CARRIER.SLA | Carrier SLA & Tender | Define SLAs and run mini-tender for lanes. | Operations | Logistics & Warehousing | Client (Logistics) | Implementation | SLA matrix; awarded lanes | OT ship ≥ 96% | LOG.OT_SHIP% | 10 | Contracts; SLAs | LOG.OT_SHIP% | Plan Monitor | Market rates
SaaS.ONBOARD.JOURNEY | Onboarding Journey Redesign | Define P0 activation path and comms. | Sales & CRM | SaaS/Subscription | Partner (Growth) | Implementation | Journey map; emails | Activation +10% | SaaS.ACTIVATION% | 10 | Figma; sequences | SaaS.ACTIVATION% | Plan Monitor | Dev backlog
SaaS.RENEWALS.PLAY | Renewals Playbook | Playbook for 90/60/30-day motion. | Sales & CRM | SaaS/Subscription | Client (CSM) | Training | Sequences; scorecards | GRR ≥ 92% | SaaS.GRR% | 6 | Playbook PDF | SaaS.GRR%, SaaS.NRR% | Plan Monitor | CS bandwidth
PS.RATECARD | Rate Card & Util Targets | Define rate card and utilization targets by grade. | Finance | Professional Services | Finance Lead (HQ) | Accounting Firm | Rate card; targets | Avg realization ≥ 80% | PS.UTIL% baseline | 5 | Policy; ERP config | PS.REALIZATION% | Plan Monitor | Market pricing
PS.PMO.CADENCE | PMO Cadence & Gate Reviews | Set weekly standups and gate reviews. | Reporting & Governance | Professional Services | Ops Admin (HQ) | Implementation | Calendar; templates | On-time delivery ≥ 95% | MEET.CADENCE | 2 | Minutes; checkpoints | PS.ON_TIME% | Plan Monitor | Project overload
HC.CLINICAL.PATH | Clinical Pathway Standardization | Standardize care pathways for top DRGs. | Operations | Healthcare | Client (Clinical) | Compliance | Pathway SOPs | ALOS ↓ ≥ 5% without QoS drop | HC.ALOS baseline | 20 | SOP; approvals | HC.ALOS, HC.READMIT% | Plan Monitor | Change management
HC.RCM.CLEAN | RCM Denial Clean-up Sprint | Root cause analysis and fixes for top denial codes. | Finance | Healthcare | Finance Lead (HQ) | Accounting Firm | Fix list; payer comms | Denial rate ↓ ≥ 15% | HC.DENIAL% | 10 | Tracker; emails | HC.DENIAL%, HC.DAYS_AR | Plan Monitor | Payer policies
HSP.REV_MGMT | Revenue Management Setup | Deploy RM rules for pricing & inventory. | Sales & CRM | Hospitality | Partner (RM) | Implementation | Rules; dashboards | RevPAR +5% in 60 days | HSP.ADR, HSP.OCC% | 7 | Config; report | HSP.REVPAR | Plan Monitor | Seasonality
HSP.FB.COSTING | F&B Recipe Costing & Wastage | Standardize recipes and track wastage. | Operations | Hospitality | Client (F&B) | Implementation | Recipes; waste SOP | Food cost ↓ ≥ 2 pts | HSP.FOOD_COST% | 6 | BOM; logs | HSP.FOOD_COST% | Plan Monitor | Chef adoption
RE.LEASE.AUDIT | Lease Data Audit | Audit lease data (rates, terms, escalations). | Data & Integration | Real Estate | Partner (Compliance) | Compliance | Audit report; corrections | Data accuracy ≥ 98% | INT.MAP.MASTER | 5 | Audit sheets | RE.OCC%, RE.RENT_COLL% | Plan Monitor | Legacy contracts
RE.CREDIT.CONTROL | Tenant Credit Control | Credit checks and dunning schedules. | Finance | Real Estate | Finance Lead (HQ) | Accounting Firm | Dunning letters; schedules | Collection rate ≥ 95% | RE.RENT_COLL% | 4 | Letters; logs | RE.RENT_COLL% | Plan Monitor | Legal limits
BANK.NPL.RECOV | NPL Recovery Program | Segment NPLs and define recovery strategies. | Finance | Banking | Client (Risk) | Compliance | Recovery playbook | NPL ratio ↓ by 50bps | BANK.NPL% | 20 | Playbook; trackers | BANK.NPL% | Plan Monitor | Legal timelines
BANK.CTI.INIT | Cost-to-Income Optimization | Ops cost review and automation backlog. | Operations | Banking | Partner (Ops) | Implementation | Backlog; savings plan | CTI ↓ ≥ 1 pt | BANK.CTI% | 15 | Business cases | BANK.CTI% | Plan Monitor | Change fatigue
CNS.BASELINE.EVM | EVM Baseline Setup | Set BAC, PV curve, and coding structure. | Reporting & Governance | Construction | Client (PMO) | Implementation | Baseline; WBS | SPI & CPI compute without gaps | CNS.PCT_COMPLETE% | 6 | WBS; baseline file | CNS.CPI, CNS.SPI | Plan Monitor | Scope changes
CNS.HSE.PROGRAM | HSE Program Rollout | TRIR reduction initiatives and toolbox talks. | Operations | Construction | Client (HSE) | Compliance | HSE calendar; logs | TRIR ↓ ≥ 10% | CNS.TRIR | 10 | HSE reports | CNS.TRIR | Plan Monitor | Site adherence
TEL.NET.OPT | Network Optimization Sprint | Reduce call drops and improve coverage. | Operations | Telecom | Client (Network) | Implementation | Optimization plan; KPIs | Call drop ↓ ≥ 20% | TEL.CALL_DROP% | 12 | Drive test reports | TEL.CALL_DROP%, TEL.NET_AVAIL% | Plan Monitor | Spectrum limits
TEL.RETENTION.PLAY | Retention Playbook | Offer engine & save desk scripts. | Sales & CRM | Telecom | Client (CX) | Training | Scripts; offers | Churn ↓ ≥ 50bps | TEL.CHURN% | 6 | Scripts; dashboards | TEL.CHURN% | Plan Monitor | Offer cost
EDU.CURRIC.REV | Curriculum Review & Mapping | Align curriculum to outcomes and accreditation. | Operations | Education | Client (Academic) | Training | Mapped curriculum | Accreditation gaps ≤ 5% | EDU.GRAD_RATE% | 20 | Mapping docs | EDU.GRAD_RATE% | Plan Monitor | Faculty availability
EDU.PLACEMENT.CELL | Placement Cell Activation | Set employer outreach and tracking. | Sales & CRM | Education | Client (Career) | Implementation | Employer list; CRM setup | Placement rate +10% YoY | EDU.PLACEMENT% | 10 | CRM exports | EDU.PLACEMENT% | Plan Monitor | Employer response
UTL.OUTAGE.MGMT | Outage Management Process | Define SAIDI/SAIFI reduction initiatives. | Operations | Utilities & Energy | Client (Ops) | Implementation | Outage SOP; crews plan | SAIDI ↓ vs baseline | UTL.SAIDI, UTL.SAIFI | 12 | SOP; KPIs | UTL.SAIDI, UTL.SAIFI | Plan Monitor | Weather risk
UTL.LOAD_MGMT | Load Management & Demand Response | Improve load factor via DR programs. | Operations | Utilities & Energy | Client (Planning) | Implementation | DR plan; customer list | Load factor +2 pts | UTL.LOAD_FACTOR% | 15 | Program docs | UTL.LOAD_FACTOR% | Plan Monitor | Customer adoption
AG.IRR.SCHED | Irrigation Scheduling | Implement precision irrigation schedules. | Operations | Agriculture | Client (Farm) | Implementation | Schedules; sensors | Water-use efficiency ↑ | AG.WATER_EFF | 7 | Sensor logs | AG.WATER_EFF | Plan Monitor | Hardware failures
AG.POSTHARV.PROG | Post-Harvest Loss Program | Improve handling and storage. | Operations | Agriculture | Partner (Ops) | Implementation | SOP; storage upgrade | Loss ↓ ≥ 20% | AG.POST_HARVEST% | 12 | Photos; logs | AG.POST_HARVEST% | Plan Monitor | Infrastructure limits
O&G.PM.OPT | Production Maintenance Optimization | Optimize PM for wells/equipment. | Operations | Oil & Gas | Client (Ops) | Implementation | PM plan; spares list | Lifting cost ↓ | O&G.LIFT_COST | 14 | Work orders; KPIs | O&G.LIFT_COST | Plan Monitor | Field access
O&G.FLARE.REDUCE | Flare Reduction Initiative | Projects to capture gas and reduce flaring. | Compliance | Oil & Gas | Client (HSE) | Compliance | Project list; permits | Flare rate ↓ vs baseline | O&G.FLARE% | 30 | Permits; reports | O&G.FLARE% | Plan Monitor | Regulatory approvals
NPO.GRANT.CYCLE | Grant Cycle Setup | Define grant calendar and reporting. | Reporting & Governance | Non-Profit | Client (Programs) | Training | Calendar; templates | On-time reports 100% | NPO.PROG_EXP% | 5 | Templates | NPO.PROG_EXP% | Plan Monitor | Donor changes
NPO.DONOR.CRM | Donor CRM & Retention Flows | Set nurture sequences for donors. | Sales & CRM | Non-Profit | Partner (CRM) | Implementation | Workflows; emails | Donor retention +5 pts | NPO.DONOR_RET% | 7 | CRM export | NPO.DONOR_RET% | Plan Monitor | Consent/opt-in